## Sheet1
Index | Task | Activities | Start Date | End Date | Status | RAG | Remarks
1 | Requirements analysis
1.1 | Determine the analytics purpose and outputs | Build statistical and machine learning models to predict fraud. Deliverables: 1) Workbook with data analytics and modelling; 2) Interactive Tableau Public dashboard; 3) Model Risk Management and Model Governance documentation; 4) (Optional) PowerPoint deck presentation. | 2026-02-09 | 2026-02-09 | Done | G
1.2 | Data collection | Collect the Feedzai Bank Account Fraud data released on Kaggle. | 2026-02-09 | 2026-02-09 | Done | G
2 | Exploratory Data Analysis (EDA)
2.1 | Data exploration | Read the data, explore data types, etc. | 2026-02-09 | 2026-02-10 | Done | G
2.2 | Statistical analysis - numeric |  | 2026-02-10 | 2026-02-10 | Done | G
2.3 | Statistical analysis - categorical |  | 2026-02-11 | 2026-02-12 | Done | G
2.4 |  |  | 2026-02-12 | 2026-02-13 | Done | G
3 | Missing value analysis
3.1 | Data exploration |  | 2026-02-14 | 2026-02-15 | Done | G
3.2 | Chi-square test of independence |  | 2026-02-15 | 2026-02-15 | Done | G
4 | Univariate analysis
4.1 | Numeric variables | Boxplot | 2026-02-14 | 2026-02-14 | Done | G
4.1.1 |  |  | 2026-02-14 | 2026-02-14 | Done | G
4.2 | Categorical variables | Barplots | 2026-02-15 | 2026-02-15 | Done | G
4.3 |  |  | 2026-02-14 | 2026-02-14 | Done | G
5 | Feature engineering
5.1 | Train tests plit |  | 2026-02-15 | 2026-02-16 | Done | G
5.2 | Missing value treatment |  | 2026-02-16 | 2026-02-17 | On track | R
5.3 | One-hot encoding |  | 2026-02-16 | 2026-02-17 | On track | A
6 | Logistic Regression
6.1 | [5 empty] | G
6.2 | [5 empty] | G
6 | XGBoost
6.1 | [5 empty] | G
6.2 | [5 empty] | G
6 | Documentation
6.1 | [5 empty] | G
6.2 | [5 empty] | G
6 | Interactive Dashboard
6.1 | [5 empty] | G
6.2 | [5 empty] | G